## Bug and New requirement
Project:	Lasooo Travel

Milestone:
Oct, 10 2011	Startup “Lasooo Travel” project

Bug and New Requirement List
Date	Status	Type	Priority	Description
Jul, 5 2012	waiting	bug	normal	Activities list page need design in city and area page.http://www.lasooo.lo/cities/%E6%88%90%E9%83%BD
Jul, 5 2012	waiting	bug	normal	The scrolling controller of activity photos list is disabled in activity detail page.
Jul, 5 2012	waiting	bug	normal	Anonymous user can publish activity diary and upload photos.
Jul, 5 2012	waiting	requirement	high	There are more functionality should be development in “My Home” page.
Jul, 5 2012	waiting	bug	normal	The first page after user login is incorrect.

## Schedule-2012
Task list in 2012

Date	Status	Type	Due Time	Start Time	Description
July
Jul, 5	order	Requirement		Jul, 5 01:30	“Joined Activity” functionality / List all I joined activity in “Joined Activity” page. And member can view the activity order information.
Jul, 5	order	Requirement		undefined	“Favorite Activity” functionality / User can add favorite activity or remove favorite activity. And list all favorite activity with latest update information in My Home->Activity->Favorite Activity page.
Jul, 5	order	Requirement		undefined
Aug, 3	order	Update		Aug, 3	Update scroll mode to static mode for extension logos of activity.

## Research and Design
Research and Design

Date	Project	Document Location	Description